## Sheet1
Task | Start | Finish | Complete in _days
Set-up and initial experiments (first year) | 2024-05-01 | 2024-08-01 | 92
1) GIS tools and initial analysis | 2024-05-01 | 2024-05-30 | 29
2) Gas analysis and biofertilizers findings | 2024-07-01 | 2024-10-01 | 92
3) Microbial, physico-chemical analysis | 2024-05-01 | 2025-04-30 | 364
Reporting-I | 2025-05-01 | 2025-05-10 | 9
Continuation of experiments (second year) | 2025-05-01 | 2025-08-01 | 92
1) GIS tools and initial analysis | 2025-05-01 | 2025-05-30 | 29
2) Gas analysis and biofertilizers findings | 2025-07-01 | 2025-10-01 | 92
3) Microbial, physico-chemical analysis | 2025-05-01 | 2026-04-30 | 364
Reporting-II | 2026-05-01 | 2026-05-10 | 9
Continuation of experiments (third year) | 2026-05-01 | 2026-08-01 | 92
1) GIS tools and initial analysis | 2026-05-01 | 2026-05-30 | 29
2) Gas analysis and biofertilizers findings | 2026-07-01 | 2026-10-01 | 92
3) Microbial, physico-chemical analysis | 2026-05-01 | 2027-04-30 | 364
Project wrapping and Reporting-III | 2027-05-01 | 2027-05-10 | 9

## extra
Biofertilizer experiments and analysis
Synthesis and dissemination
1) present findings at Conferences
Biofertilizer experiments and analysis
Synthesis and dissemination
1) present findings at Conferences
2) draft research papers and reports
3) consider practical application of findings
| Reporting-II | 2026-05-01
Validation and conclusion
Project wrapping and reporting-III